SCHEDULE FOR APPLICATION AND APPROVAL OF

FY 2013 CIP ENERGY EFFICIENCY INITIATIVE (FY13 CIP-EEI)

5/8/12	FY13 CIP-EEI Draft Administrative Procedures issued to LEAs for comment

5/10/12	LEA Facility Planners Meeting, Edgewood High, Harford County

Afternoon session: Presentation of FY13 CIP-EEI by PSCP and MEA, LEA workshops with utilities, Q&A on eligibility, application process, etc.

5/23/12	Board of Public Works approval of FY 2013 CIP, inclusive of $25 million reserved for FY13 CIP-EEI.

6/15/12	Release of FY13 CIP-EEI Incentive Applications, Incentive Calculators, and “Final Draft for IAC Approval” of Administrative Procedures.

6/21/12	Seminar to explain program standards and application forms; initiation of application process.

Late June	LEA consultation with MEA and PSCP on program and project

to early August 	requirements, as requested.

7/17/12	Pre-FY 2014 CIP Seminar, Annapolis, MD;

Discussion, clarification of FY13 CIP-EEI applications

8/7/12	Applications due for preliminary screening of FY13 CIP-EEI projects, including both approved FY 2013 CIP projects for recalculation of State participation, and prospective FY 2014 CIP projects (FY13 CIP-EEI eligible only)

Late July to	PSCP/MEA staff review of preliminary screening applications

end of August 	and meetings with LEAs as needed to clarify requirements

10/5/12	Submission of:

- FY 2014 CIP requests;

- Requests for recalculation of State funding participation for approved FY 2013 CIP projects.

11/10/12	Staff presentation to IAC of preliminary FY 2014 CIP recommendations, inclusive of FY13 CIP-EEI funds for eligible projects.

12/4/12	IAC hearing on FY 2014 CIP requests, inclusive of FY13 CIP-EEI funding.

12/31/12	Submission of IAC recommendations for 75% of preliminary FY 2014 funding, inclusive of FY13 CIP-EEI funds as appropriate.

1/23/13	BPW approval of 75% of preliminary FY 2014 funding, inclusive of amendment to FY 2013 CIP for approved FY13 CIP-EEI projects

January to May	Periodic approvals by BPW of amendments to FY 2013 CIP for recalculation of approved FY 2013 projects to include FY13 CIP-EEI funding

May 2013 (TBD)	Final BPW approval of FY 2014 CIP, as well as of final amendment to FY 2013 CIP for approved FY13 CIP-EEI projects

7/31/13	All FY13 CIP-EEI project funds to be encumbered

August 2013	Funds for FY13 CIP-EEI projects to be substantially expended

August 2014	FY13 CIP-EEI projects to be substantially completed and the majority of funds expended